## Gantt
System Name	AcadeMate
Members:
Franchesca Louise R. Abella
Paul Abellana
Kyle Sumucad

Legend:		Todo
		In-Progress
		Done
		On-hold
					September				October				November
Tasks	Assignee	Date Started	Date Finished	Status	1	2	3	4	1	2	3	4	1	2	3	4
1. Functional Requirements
User Registration	Sumucad	10/12/2024	10/15/2024
User Login	Abella	10/12/2024	10/16/2024
Task Management	Abellana	10/15/2024	10/19/2024
Expense Recording	Sumucad	10/01/2024	10/20/2024
Deadline Tracking	Abellana	10/15/2024	11/12/2024
Logout	Abella	10/12/2024	11/15/2024
Home UI	Sumucad	10/13/2024	10/23/2024
Navigation	Abella	10/11/2024	10/25/2024
Journal	Abellana	10/28/2024	11/16/2024