## Gantt
System Name | AcadeMate
Members:
Franchesca Louise R. Abella
Paul Abellana
Kyle Sumucad
Legend: |  | Todo
In-Progress
Done
On-hold
[5 empty] | September |  |  |  | October |  |  |  | November
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Functional Requirements
User Registration | Sumucad | 2024-10-12 | 2024-10-15
User Login | Abella | 2024-10-12 | 2024-10-16
Task Management | Abellana | 2024-10-15 | 2024-10-19
Expense Recording | Sumucad | 2024-10-01 | 2024-10-20
Deadline Tracking | Abellana | 2024-10-15 | 2024-11-12
Logout | Abella | 2024-10-12 | 2024-11-15
Home UI | Sumucad | 2024-10-13 | 2024-10-23
Navigation | Abella | 2024-10-11 | 2024-10-25
Journal | Abellana | 2024-10-28 | 2024-11-16